## Construction Log
From (LF) | To (LF) | Quantity (LF) | Unit (LF) | Description of Work | Existing | Comments | Pay Item | Drawing #
| 0+00 | 1 | EA | Install Culvert w/ headwalls |  | 18"-24" Black, Double Wall PVC. Pking lot work will change this culvert. | 92103 | 921-20-01
0+00 | 21+00 | 2100 | LF | Trail Construction-Clearing & Grubbing |  | Expanding the parking lot ~10' or so will shorten the finished length of the trail. | 91202 | 912-01 912-02
0+00 | 21+00 | 2100 | LF | Trail Construction-Excavation |  |  | 91101 | 911-01 911-02
0+00 | 21+00 | 2100 | LF | Install Crushed Aggregate Surfacing |  | 4" Deep x 5' wide, 5/8"-, Crushed Limestone, Machine Compacted | 91301 | 913-01
| 0+45 |  |  |  | Stone Choke Point | Keep existing rocks, surface between them. Keep as much moss on the rocks as possible.
1+15 | 1+65 | 50 |  | Install Turnpike, No Ditches |  |  | 93201 | 932-20-01
2+60 | 2+95 | 50 |  | Install Puncheon |  | See Drawing. T-Shaped Puncheon @ intersection. 2+95 is junction with picnic site, puncheon extends 10' towards picnic area and 5' to the right, past 2+96. | 93801 | 938-10-01 938-10-03
| 2+95 |  |  |  | Jct. to Picnic Sites | 2+95 is junction with first picnic site, puncheon extends 10' towards picnic and 5" past 2+96
5+20 | 5+50 | 30 |  | Install Turnpike |  | Double Ditches | 93201 | 932-20-01
| 6+70 |  |  |  | Jct. to Picnic Sites
| 9+40 |  |  |  | Jct. to Gravel Bar
14+40 | 15+00 | 60 |  | Install Rock Crib Wall |  | 60' x 2' = 120 SFF | 93501 | 935-20-01
15+30 | 15+55 | 25 |  | Install Turnpike |  | Double Ditches | 93201 | 932-20-01
15+55 | 16+00 | 45 |  |  | Rootwad/Borrow
18+80 | 19+30 | 50 |  | Install Puncheon |  |  | 93801 | 938-10-01 938-10-03
19+30 | 20+30 | 100 |  | Install Turnpike |  | No Ditches |  | 932-20-01
| 21+00 |  |  |  | Jct. With Loop
Picnic Spur #1 - Right to Picnic Site #1
| 0+00 |  |  |  | Sta. 0+00 = Sta. 2+95
0+00 | 0+15 | 15 | LF | Trail Construction - Clearing and Grubbing |  | 5' Wide Trail |  | 912-01 912-02
0+00 | 0+15 | 15 | LF | Trail Construction - Excavation |  | Excavated Section |  | 911-01 911-02
0+00 | 0+15 | 15 | LF | Install Crushed Aggregate Surfacing |  | 5' Wide Trail. 5/8"-, Crushed Limestone, Machine Compacted |  | 913-01
| 0+15 | 150 | SF | Picnic Site #1 - Clearing, Grubbing, & Excavation. | Camp site and Fire Ring | 15' x 10' = 150 SF. | 91101 91202 | 911-01 911-02 912-01 912-02
| 0+15 | 150 | SF | Install Crushed Aggregate Surfacing | Picnic Site #1 | 15' x 10' = 150 SF. 5/8"-, Crushed Limestone, Machine Compacted |  | 913-01
Picnic Spur #2 - Straight to Picnic Sites 2 & 3
| 0+00 |  |  |  | Sta. 0+00 = Sta. 2+95
0+00 | 1+35 | 135 | LF | Trail Construction - Clearing and Grubbing |  | 5' Wide Trail |  | 912-01 912-02
0+00 | 1+35 | 135 | LF | Trail Construction - Excavation |  |  |  | 911-01 911-02
0+00 | 1+35 | 135 | LF | Install Crushed Aggregate Surfacing |  | 15' x 10' = 150 SF. 5/8"-, Crushed Limestone, Machine Compacted |  | 913-01
| 1+00 | 600 | SF | Picnic Site #2 - Clearing, Grubbing, & Excavation. |  | 30' x 20' = 600 SF |  | 911-01 911-02 912-01 912-02
| 1+35 | 300 | SF | Picnic Site #3 - Clearing, Grubbing, & Excavation. |  | 30' x 20' = 600 SF |  | 911-01 911-02 912-01 912-02
| 1+00 & 1+35 | 900 | SF | Install Crushed Aggregate Surfacing | Picnic Sites #2 & #3 | 5/8"-, Crushed Limestone, Machine Compacted |  | 913-01
Picnic Spur #3 - Left to Picnic Sites 4 & 5
| 0+00 |  |  |  | Sta. 0+00 = Sta. 6+70
0+00 | 1+10 | 110 | LF | Trail Construction - Clearing and Grubbing |  | 5' Wide Trail |  | 912-01 912-02
0+00 | 1+10 | 110 | LF | Trail Construction - Excavation |  |  |  | 911-01 911-02
0+00 | 1+10 | 110 | LF | Install Crushed Aggregate Surfacing |  | 5/8"-, Crushed Limestone, Machine Compacted |  | 913-01
| 0+90 | 400 | SF | Picnic Site #4- Clearing, Grubbing, & Excavation. |  | 20' x 20' = 400 SF |  | 911-01 911-02 912-01 912-02
| 1+10 | 300 | SF | Picnic Site #5 - Clearing, Grubbing, & Excavation. |  | 20' x 15' = 600 SF |  | 911-01 911-02 912-01 912-02
| 1+10 | 100 | SF | Picnic Site #6 - Clearing, Grubbing, & Excavation. |  | 10' x 10' = 100 SF |  | 911-01 911-02 912-01 912-02
| 0+90, 1+10, & 1+10 | 800 | SF | Install Crushed Aggregate Surfacing | Picnic Sites #4, #5, #6 | 5/8"-, Crushed Limestone, Machine Compacted |  | 913-01
Picnic Spur #4 - Left to Picnic Sites #7
| 0+00 |  |  |  | Sta. 0+00 = Sta. 9+85
0+00 | 0+60 | 60 | LF | Trail Construction - Clearing and Grubbing |  | 5' Wide Trail |  | 912-01 912-02
0+00 | 0+60 | 60 | LF | Trail Construction - Excavation |  |  |  | 911-01 911-02
0+00 | 0+60 | 60 | LF | Install Crushed Aggregate Surfacing |  | 5/8"-, Crushed Limestone, Machine Compacted |  | 913-01
| 0+60 | 225 | SF | Picnic Site #7- Clearing, Grubbing, & Excavation. |  | 15' x 15' = 225 SF |  | 911-01 911-02 912-01 912-02
| 0+60 | 225 | SF | Install Crushed Aggregate Surfacing | Picnic Sites #7 | 5/8"-, Crushed Limestone, Machine Compacted |  | 913-01
Picnic Spur #5 - Left to Picnic Sites #8
| 0+00 |  |  |  | Sta. 0+00 = Sta. 11+95 | Site is directly adjacent to the trail.
| 0+60 | 225 | SF | Picnic Site #7- Clearing, Grubbing, & Excavation. |  | 15' x 15' = 225 SF |  | 911-01 911-02 912-01 912-02
| 0+60 | 225 | SF | Install Crushed Aggregate Surfacing | Picnic Sites #8 | 5/8"-, Crushed Limestone, Machine Compacted |  | 913-01
Picnic Spur #6 - Left to Picnic Sites #9
| 12+55 |  |  |  | Burned Site | Site is directly adjacent to the trail.
| 12+55 | 1000 | SF | Picnic Site #8- Clearing, Grubbing, & Excavation. |  | 40' x 25' = 1000 SF |  | 911-01 911-02 912-01 912-02
| 12+55 | 1000 | SF | Install Crushed Aggregate Surfacing | Picnic Sites #8 | 5/8"-, Crushed Limestone, Machine Compacted |  | 913-01
Beach Access Spur Trail
| 0+00 |  |  |  | 0+00 = 6+70
0+00 | 2+22 | 222 | LF | Trail Construction - Clearing & Grubbing |  | 4' Wide |  | 912-01 912-02
0+00 | 2+22 | 222 | LF | Trail Construction - Excavation |  | 4' Wide |  | 911-01 911-02
0+00 | 2+22 | 222 | LF | Install Crushed Aggregate Surfacing |  | 5/8"-, Crushed Limestone, Machine Compacted |  | 913-01
1+10 | 1+20 | 10 | LF | Install Crib Ladder Stairway |  | -18% |  | 936-20-01
| 1+20 | 1 | EA | Stairway Landing |  |  |  | 936-20-01
1+20 | 1+32 | 12 | LF | Install Crib Ladder Stairway |  | -37% |  | 936-20-01